## Project Schedule
PROJECT SCHEDULE TEMPLATE
Library Book Catalog | Alex M., Brooke W. Harshitha V.
A comprehensive system for managing a library's inventory. Allows registered users to checkout,return,or place holds on books and manages waitlists. Only users with admin permissions can make destructive changes such as modifying inventory content. GUI allows users to easily make checkout/hold requests, view relevant information (eg, waitlist position for a book), and search for items in the library's inventory by title, author, tags, etc.
SCOPE STATEMENT
START DATE | END DATE | OVERALL PROGRESS
2025-10-01 | 2025-12-03 | 45%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Core Functionality (Checkout/Return/Waitlist) | Alex | 2025-10-23 | 2025-10-27 | 2 | Complete
Bug Fixes to Core Features | Everyone | 2025-10-27 | 2025-10-29 | 2 | Complete
Team Meeting | Everyone | 2025-10-29 | 2025-10-29 | N/A | Complete
Testing - Core Functions |  | 2025-10-29 | 2025-11-14 | 16 | Not Started
Persistence (Save File) | Brooke | 2025-10-29 | 2025-11-03 | 6 | Complete
Updates to Persistence | Brooke | 2025-11-04 | 2025-11-21 | 17 | Not Started | Expand catalog_system() to track waitlist/pending holds. Make a new method which actually recreates the current state of the library from the save file at program start (ie, checking out books, rebuilding waitlist, etc
Iteration #4 Submission | Everyone | 2025-11-21 | 2025-11-21 | N/A | Not started
Inventory Search (Search by title, author, genre) | Harshitha | 2025-11-04 | 2025-11-21 | 17 | In Progress
User/Admin Permissions | Alex | 2025-11-04 | 2025-12-01 | 27 | In Progress | Design a system to assign roles to users (ie, member/admin), and control which permissions they have in the library system. For example, users can checkout,return,search, but only admins can add/remove books from the inventory.
Recommendation Feature | Harshitha | 2025-11-04 | 2025-11-21 | 17 | Not Started
Design GUI (version 1) |  | 2025-11-21 | 2025-12-01 | 10 | Not Started
Incorporate GUI into main project |  | 2025-11-21 | 2025-12-01 | 10 | Not Started
Presentation | Everyone | 2025-11-21 | 2025-12-03 | 12 | Not Started